## Sheet1
PROJECT PLAN + TASK SHEET
| Subject: | PRJ321
| Class: | SE1402
| Project: | ATM System
| Group: | 7
| Members: | Nguyen Huu Duy | DuyNH | CE140596 | duynhce140596@fpt.edu.vn
|  | Truong Thanh Toan | ToanTT | CE140640 | toanttce140640@fpt.edu.vn
|  | Ta Nguyen Thuy Vy | VyTNT | CE140626 | vytntCE140626@fpt.edu.vn
| Repository: | https://github.com/nh-duy/PRJ321_G7
No. | Assigned task | PIC | Start | End | Task completion
1 | Design use-case diagram | DuyNH, ToanTT, VyTNT | 2020-05-28 | 2020-06-01 | 100%
2 | Design database | DuyNH, VyTNT | 2020-06-01 | 2020-06-07 | 100%
3 | Design class diagram | DuyNH | 2020-06-08 | 2020-06-09 | 100%
4 | Select application architecture | DuyNH | 2020-06-09 | 2020-06-13 | 100%
9 | Write documentation | DuyNH, ToanTT | 2020-06-09 | 2020-06-15 | 100%
5 | Implement backend - Customer | VyTNT | 2020-06-15 | 2020-07-05 | 100%
6 | Implement backend - Employee | ToanTT | 2020-06-15 | 2020-07-05 | 100%
7 | Implement backend - Admin | DuyNH | 2020-06-15 | 2020-07-05 | 100%
8 | Implement fully frontend - Client + UI | DuyNH | 2020-07-01 | 2020-07-19 | 100%
10 | Write user manual | ToanTT, VyTNT | 2020-07-20 | 2020-07-21 | 100%